## Sprint 1
Sprint 1 | # Team Members | 4 | Used for hours burn down (not as many teams do this these days)
| # Hours in 1 work day | 6 | Used for hours burn down (not as many teams do this these days)
| # Days in this sprint | 4 | Total number of work days in Sprint (exclude public holidays etc)
Hours | Day | 1 | 2 | 3 | 4
| Available | 96 | 72 | 48 | 24 | 0
| Task Hrs Remaining | 96 | 67 | 43 | 37 | 6

## Sprint 2
Sprint 2 | # Team Members | 4 | Used for hours burn down (not as many teams do this these days)
| # Hours in 1 work day | 6 | Used for hours burn down (not as many teams do this these days)
| # Days in this sprint | 4 | Total number of work days in Sprint (exclude public holidays etc)
Hours | Day | 1 | 2 | 3 | 4
| Available | 96 | 72 | 48 | 24 | 0
| Task Hrs Remaining | 96 | 80 | 50 | 24 | 0

## Sprint 3
Sprint 3 | # Team Members | 4 | Used for hours burn down (not as many teams do this these days)
| # Hours in 1 work day | 6 | Used for hours burn down (not as many teams do this these days)
| # Days in this sprint | 4 | Total number of work days in Sprint (exclude public holidays etc)
Hours | Day | 1 | 2 | 3 | 4
| Available | 96 | 72 | 48 | 24 | 0
| Task Hrs Remaining | 110 | 100 | 46 | 10 | 0

## Sprint 4
Sprint 4 | # Team Members | 4 | Used for hours burn down (not as many teams do this these days)
| # Hours in 1 work day | 6 | Used for hours burn down (not as many teams do this these days)
| # Days in this sprint | 4 | Total number of work days in Sprint (exclude public holidays etc)
Hours | Day | 1 | 2 | 3 | 4
| Available | 96 | 72 | 48 | 24 | 0
| Task Hrs Remaining | 96 | 91 | 45 | 28 | 8

## Sprint 5
Sprint 5 | # Team Members | 4 | Used for hours burn down (not as many teams do this these days)
| # Hours in 1 work day | 6 | Used for hours burn down (not as many teams do this these days)
| # Days in this sprint | 4 | Total number of work days in Sprint (exclude public holidays etc)
Hours | Day | 1 | 2 | 3 | 4
| Available | 96 | 72 | 48 | 24 | 0
| Task Hrs Remaining | 105 | 91 | 30 | 8 | 0