## Product Backlog
ID | Priority | Estimated Time (hours) | User Story | Status
3 | Critical | 60 | As a renter, I want to be able to search through listings by different categories, ratings, or name so that I can more easily find a game that I want. | Completed
1 | Critical | 60 | As a renter, I want to be able to rent games that I have access to for a specified amount of time, so that I can play them. | Completed
2 | Critical | 10 | As a renter, I want to be able to return rented games, so that I can rent new ones. | Completed
4 | High | 40 | As an administrator I want to be able to add new items to the list so that the system displays up to date representation of the inventory. | Completed
5 | High | 60 | As a renter, I want to login using a username and a password, so I can access the system on my own account on the server. | Completed
6 | High | 20 | As a renter, I want to review my currently rented games, so that I can see if I can rent more games. | Completed
7 | High | 16 | As an administrator I want to be able to change information about the existing items so that the system displays up to date information. | Completed
8 | High | 20 | As an administrator I want to be able to remove games that are no longer in stock so that the system only shows items that are in stock. | Completed
9 | High | 40 | As a renter, I want to be able to register using my contact information including email, address, full name, date of birth, username, and password, so that I can have my own account on the system. | Completed
10 | Medium | 16 | As an administrator, I want to be able to edit the renter information so they match the real world information. | Completed
11 | Medium | 26 | As an admininstrator, I want to be able to terminate renters in order to prevent and punish fraud. | Completed
12 | Low | ? | As a renter, I want to leave ratings for games I rented, to give feedback for other renters to view. | Completed
13 | Low | 26 | As a renter, I want to pay for my subscription and for any arising late fees,so that I can use the platform. | Completed
14 | Low | ? | As an administrator, I want to be able to issue a refund for an unsatisfied customer so that they want to continue using our services. | Completed
15 | Low | 16 | As a renter, I want to have an easy to understand user guide, so that I can best use of the features available. | Completed
16 | Low | ? | As an administrator, I want to be able to fine renters, so that I can discourage late returns. | Completed
17 | Low | 32 | As an administrator, I want to revoke renting priveledges of renters, so that only trusted renters have access to the system. | Completed
18 | Low | 26 | As a renter, I want to be able to see the balance on my account, so I can make payments. | Completed

## Sprint Backlog
PB ID | Task Title | Comments | Responsible | Estimate | Status | Sprint # | Start | Finish
1 | Model that can rent games | Games plural, rented boolean | Martin | 20 | Completed | 1 | 2022-04-20 | 2022-05-04
6 | Automated update to check of rental period | Counter of decreasing days | Chris | 4 | Completed | 1 | 2022-04-20 | 2022-05-04
1 | Define console commands | Login (admin or user), add game, rent game | Kruno | 4 | Completed | 1 | 2022-04-20 | 2022-04-27
5 | Barebones login | Username only | Lev | 4 | Completed | 1 | 2022-04-20 | 2022-04-27
4 | Model that can add games | Single user | Lev, Kruno | 12 | Completed | 1 | 2022-04-20 | 2022-04-27
3 | List games available in console | Not the whole user story included, just a printout of games | Kruno | 8 | Completed | 1 | 2022-04-20 | 2022-04-27
1 | Basic client server split | After other items are completed (Very challenging) | Everyone | 25 | Completed | 1 | 2022-04-27 | 2022-05-10
| Write initial unit tests | Part of test driven development | Lev, Kruno | 6 | Completed | 1 | 2022-04-27 | 2022-05-05
| Write comments in ceremony notes and log meetings |  | Chris | 6 | Completed | 1 | 2022-04-20 | 2022-05-10
| Write javadoc explaining methods |  | Everyone | 6 | Completed | 1 | 2022-04-20 | 2022-05-11
| Create Github repo |  | Chris | 1 | Completed | 1 | 2022-04-20 | 2022-04-27
| FXMLs in Scene builder | See Blink 182 | Kruno, Chris | 20 | Completed | 2 | 2022-05-10 | 2022-05-13
| Diagram navigation of GUI | Login, signup, search, manage user, admin interface (password: admin) | Martin | 10 | Completed | 2 | 2022-05-10 | 2022-05-11
| Create controllers, creator, and viewhandler | Copy base of exercise | Kruno, Chris | 24 | Completed | 2 | 2022-05-10 | 2022-05-16
| Viewmodel to connect | Methods in model too | Lev | 20 | Completed | 2 | 2022-05-10 | 2022-05-16
9 | Add alerts for confirmation | Deleting and adding games and users | Chris, Martin | 10 | Completed | 2 | 2022-05-13 | 2022-05-16
| Connect exceptions to the error labels | Keep in mind custom exceptions | Lev | 10 | Completed | 2 | 2022-05-10 | 2022-05-13
| Create new main method to start the application and client | Additional test class to use debugger out of GUI | Kruno | 2 | Completed | 2 | 2022-05-10 | 2022-05-12
4 | ER diagram first draft | See domain model | Chris | 5 | Completed | 3 | 2022-05-16 | 2022-05-18
4 | Global relation first draft |  | Kruno | 5 | Completed | 3 | 2022-05-18 | 2022-05-18
4 | Relational schema |  | Kruno | 3 | Completed | 3 | 2022-05-18 | 2022-05-18
4 | Creation of the tables |  | Chris | 8 | Completed | 3 | 2022-05-18 | 2022-05-18
4 | Constrainsts |  | Chris | 10 | Completed | 3 | 2022-05-16 | 2022-05-20
4 | Queries to test |  | Lev, Martin | 13 | Completed | 3 | 2022-05-16 | 2022-05-20
18 | Balance user side | Payment and adding balance | Lev, Martin | 5 | Completed | 3 | 2022-05-16 | 2022-05-17
14 | Refund |  | Lev, Martin | 5 | Completed | 3 | 2022-05-17 | 2022-05-18
16 | Fine |  | Lev, Martin | 6 | Completed | 3 | 2022-05-17 | 2022-05-18
17 | Revoke user priveledge |  | Lev, Martin | 9 | Completed | 3 | 2022-05-17 | 2022-05-18
12 | Ratings |  | Lev, Martin | 13 | Completed | 3 | 2022-05-17 | 2022-05-18
12 | Terminate user |  | Lev, Martin | 5 | Completed | 3 | 2022-05-16 | 2022-05-17
6 | Check for date using triggers | All triggers | Chris | 5 | Completed | 3 | 2022-05-16 | 2022-05-20
14 | Transactions table | Create transactionDAO and implement | Kruno | 5 | Completed | 3 | 2022-05-16 | 2022-05-20
4 | Add game to a database table |  | Chris, Kruno | 8 | Completed | 3 | 2022-05-16 | 2022-05-20
6 | Retrieve the games rented by user |  | Chris, Kruno | 5 | Completed | 3 | 2022-05-17 | 2022-05-20
1 | Test cases renting game | Make sure exceptions appear correct on GUI | Martin | 3 | Completed | 4 | 2022-05-23 | 2022-05-26
10 | Test cases for users | Delete while game is rented | Martin | 3 | Completed | 4 | 2022-05-23 | 2022-05-25
7 | Tests for managing games | Delete game while it is rented |  | 3 | Completed | 4 | 2022-05-24 | 2022-05-25
1 | Look for errors where synchronized is needed |  | Everyone | 3 | Completed | 4 | 2022-05-23 | 2022-05-24
| Bug squashing | Communicate with tests. Rentals are important | Everyone | 15 | Completed | 4 | 2022-05-20 | 2022-05-23
| Javadoc up to 20/5 version |  | Everyone | 15 | Completed | 4 | 2022-05-20 | 2022-05-23
| Domain model |  | Kruno | 5 | Completed | 4 | 2022-05-23 | 2022-05-24
| Process report first draft | Methodology, team description, so on | Lev, Martin | 15 | Completed | 4 | 2022-05-20 | 2022-05-26
| Project Report: Introduction | Link from description | Chris | 5 | Completed | 4 | 2022-05-23 | 2022-05-24
| Project Report: Analysis |  | Kruno, Chris | 5 | Completed | 4 | 2022-05-24 | 2022-05-26
| Project Report: Design |  | Kruno, Chris | 5 | Completed | 4 | 2022-05-25
3 | Search function | Avengers level threat | Chris | 5 | Completed | 4 | 2022-05-20 | 2022-05-23
| Increase error label size | Make legible (Maybe alert popups) | Lev | 3 | Completed | 4 | 2022-05-25 | 2022-05-25
| Custom error text for expected exceptions |  | Lev | 8 | Completed | 4 | 2022-05-23 | 2022-05-24
| Check when error label is reset |  | Everyone | 5 | Completed | 4 | 2022-05-23
NFR | Password security |  | Lev | 6 | Completed | 5 | 2022-05-26 | 2022-05-26
| Complete JavaDocs |  | Lev | 2 | Completed | 5 | 2022-05-26 | 2022-05-26
| Process report: execution |  | Lev, Martin | 5 | Completed | 5 | 2022-05-26
| Process report: introduction |  | Everyone | 4 | Completed | 5 | 2022-05-26
| Process report: review |  | Everyone | 4 | Completed | 5 | 2022-05-26
15 | Admin guide |  | Lev | 5 | Completed | 5 | 2022-05-27
15 | User guide |  | Kruno | 5 | Completed | 5 | 2022-05-26
| Project report: requirements |  | Chris | 3 | Completed | 5 | 2022-05-26 | 2022-05-27
| Project report: design |  | Kruno | 5 | Completed | 5 | 2022-05-26
| Project report: implementation |  | Lev, Kruno | 8 | Completed | 5
| Project report: project future |  | Martin | 3 | Completed | 5
| Project report: test |  | Martin | 5 | Completed | 5 | 2022-05-26
| Project report: results |  | Martin | 5 | Completed | 5
| Project report: conclusion |  | Chris | 3 | Completed | 5
| Project report: abstract |  | Chris | 2 | Completed | 5
| Project report: sources |  | Chris | 1 | Completed | 5
| Project report: refinement | Formatting, flow, and structure | Everyone | 3 | Completed | 5
| Personal reflection |  | Everyone | 10 | Completed | 5 | 2022-05-26
| Packing deliverables | Zip and appendices | Everyone | 3 | Completed | 5
14 | Fix transactions |  | Lev | 1 | Completed | 5 | 2022-05-26 | 2022-05-27
| Easter eggs |  | Everyone | 3 | Completed | 5